## Sheet1
day | month | year | milestone
17 | 9 | 2014 | Received NIJ funding
13 | 5 | 2019 | Received NIH funding
15 | 8 | 2019 | Started participant recruitment
5 | 9 | 2019 | First F/U Interview
23 | 10 | 2020 | First LEAD Panel review
25 | 3 | 2020 | First UNC case reviewed
18 | 5 | 2020 | Final UNC case reviewed
26 | 2 | 2020 | Began LEAD panel voting in FM Pro
20 | 3 | 2020 | Stopped recruitment for COVID19
9 | 6 | 2020 | Began recruitment post-COVID 19
22 | 7 | 2020 | MedStar joins LEAD panel
31 | 1 | 2021 | Started sending the LEAD panel all F/U Interviews
21 | 4 | 2021 | LEAD Panel used the post-DETECT vote for the first time
29 | 5 | 2021 | Pilot study recruitment
11 | 9 | 2021 | DETECT visits transitioned from EMT back to MIH
19 | 4 | 2022 | In-person recruiting pilot test started
6 | 7 | 2022 | Follow up interviews with MoCA < 17 Approved by IRB
13 | 7 | 2022 | MDAC started scheduling MoCA < 17